## Project Timeline
Comparator
TIMELINE
| PROJECT DETAILS |  | Working 8hrs Mon and Fri
Steps | DATE | MILESTONE | POSITION | BASELINE | HRS |  | Initial state: | It verifies the part number, the quantity and the nomenclature associated in the 3D and 2D.
| 2013-12-20 | Project Start | -2 | 1 |  | Phase 1: 88 hrs |  | For the moment, the Comparator must be used in conjunction with
1 | 2014-01-21 | Exporting multiple 3D assy at a time | 5 | 1 | 16 |  |  | the Export BOM macro. The user must then copy and paste the 3D result from
2 | 2014-01-28 | Exporting specific assy from 2D and multiple pages | -5 | 1 | 8 |  |  | the chosen assembly, as well as the 2D result of the chosen 2D table in CATIA into
3 | 2014-02-04 | Creating a functional UI | 4 | 1 | 16 |  |  | the Excel workbook containing the Comparator macro
4 | 2014-02-11 | Creating an HTML report | -2 | 1 | 16
5 | 2014-02-18 | Enabling Batch mode | 3 | 1 | 16 |  | Limitations: | •The 3D Export takes too long sometimes up to 15 minutes and it can’t include multi-pages part lists in a single selection.
6 | 2014-02-25 | Importing Excel table to CATIA with flagnotes | 5 | 1 | 16 |  |  | •The initial exporting, copy & pasting process is too much of an hassle for the user.
7 | 2014-03-04 | Exporting hinges from lower sub assys | -4 | 1 | 8 | Phase 2: 72 hrs |  | The user can only compare one drawing and one 3D sub-assembly at a time
8 | 2014-03-04 | Generate notes based on Dwg code & matl | 2 | 1 | 8
9 | 2014-03-11 | Auto generate NPCF forms | -7 | 1 | 16 |  | New Functionalities: | •User will be able to simply select the 2D and will compare the associated direct children of that drawing
10 | 2014-04-01 | Spell check on drawings and ECNs | 4 | 1 | 24 |  |  | •User will be able to select a multi-page part list
11 | 2014-04-08 | Check for sheet number | -4 | 1 | 8 |  |  | •User will be able to have an output in multiple formats such as HTML and Excel
12 | 2014-04-08 | Deploying application to designers | 6 | 1 | 8
| Total |  |  |  | 160
1
1
1
Formulas:
DATE = [DATE, row above]+7
DATE = [DATE, row above]
Project Timeline Tips:
The role of the Position values in the Project Details table is to prevent the Milestone labels from overlapping each other on the timeline. Use positive numbers to position labels above the timeline and negative numbers to position them below.
To add additional Milestones, either insert new rows within the table or start typing below the last table entry and the table will automatically expand to accommodate your newly added data.

## ROI
Simple ROI summary for the G5000 Design group for The Comparator Macro
Metrics | Actual | Projected
Average optimal Daily output of drawing in workflow (drawings) | 20
Working days per year (day) | 252
Time to program (hrs) | 160
Average Designer Salary ($/hr) | 60
Time to execute macro (min) | 15 | 1
Time spent to use the macro in a day (hrs) | 5 | 0.33
Time spent to use the macro in a year (hrs) | 1260 | 84
Time saved with the new macro in a year (hrs) | 1176
Time saved with the new macro in a day (hrs) | 4.67
ROI =(gain from investment - cost of investment) / cost of investment=(1176-160)/160 | 635%
Payback period= ((time of investment/daily savings) + time of investment) =(160/4.67)+160 | 34 days + 20 days
Money saved per year | 70560

## Lean ROI
-Efficiency ROI for the G5000 Design group for The Comparator Macro-
Waste | Actual Problem | Projected Solution
Transport | The information is not always known at the next node in workflow. The information can get damaged” (missing a page, lost, etc.) when the paper where the marking to compare them has been done. | The information would be eventually attached to the workflow process in order to increase visibility of the work done and it is easier to communicate with people outside of the facility.
Inventory | Not Applicable | Not Applicable
Motion | There is a lot of motion that can be eliminated which are not necessary such as getting the paper from the printer and manually checking the 3D and the 2D which leads to unavoidable human errors. More motion equals to more human errors | All the motions related to the exports are reduced to only a few clicks. And all the information needed to complete the tasks is within reach.
Waiting | The code for the current macro makes it too slow. Because the work has to be done manually, the user has to be focused for this one and only task. | With a fully automated process, the user would be available to perform parallel task while he’s waiting.
Over-production | Not Applicable | Not Applicable
Over-processing | A lot of times, the user doesn’t remember if he did the work or when he did it, so he just ends doing over again. | The work can be traced to the date, to the revision or the user that did it for an easier traceability. That information can be stored to a file or a database.
Defects | Defects occur when wrong part are being called which are not necessary | Defects can be greatly reduced simply by questioning when there are mismatched parts or quantities with the 2D and 3D.

## UI
1
2
5
6
1
2
3
4
5
6
The user selects a 3D product as an input.
The user selects then select which children will be treated
The user sees in the text box his selection and select the output format to HTML
After the selection of the output is done then the user can launch the macro
After the launch, the user can see the progress of the macro
The final result, in this case, is a HTML file that gives the difference with the 2D and 3D
4
3

## Error reasons in PE node
This macro will help reduce the most common errors seen at the Project engineer node
3D vs 2D: This will catch discrenpancy between the Drawing parts list on the 3D BOM. (Step 1 to 6)
Notes: Based on the nomenclature, the dwg code and the material code & the partnumber, notes would be automatically suggested to the designer. (Step 8)
NPCF: Based on the revision, the drawing code, and the material a NPCF could be generated automatically. (Step 9)
Typo: By exporting the text from the Drawing and the ECN into Excel or Word, a spell check can be done based on a custom "C&D Montreal Dictionary". (Step 10)